## Sheet1
Project | Milestone | Screen Name | Nature of Task | Tasks | Resource | HH:MM | Predecessor | Start Date | End Date
|  |  |  | Project Setup | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-14 | 2020-01-14
| Admin Panel |  |  | Template integration for SignIn | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-14 | 2020-01-14
|  |  |  | Template integration for Forget Password | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-14 | 2020-01-14
|  |  |  | Template integration for Reset Password | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-14 | 2020-01-14
|  |  |  | Template integration for Signup | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-15 | 2020-01-15
|  |  |  | Models Creation for User Having Fields: 1. uuid UUID Field 2. Name Char Field 3. Merchant ID CharField 4. Mobile no CharField 5. Email id Email Field 6. User Type Having Choice: 6.1: Admin 6.2: Merchant 7. is_active Boolen Field 8. is_superuser Boolen Field | py-aftabhussain@mobiloitte.com | 4 |  | 2020-01-15 | 2020-01-15
|  |  |  | 2.Api Creation for Singup merchant havinf Field: 1. Name 2. Merchant Name 3. Email ID 4. Merchant ID 5. Mobile Number | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-15 | 2020-01-15
|  |  |  | Api Creation for Login with Email id and password | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-16 | 2020-01-16
|  | Dashboard |  | Template integration for Dashboard, Merchant Management, Fee Management, Admin Profile, Logout | py-aftabhussain@mobiloitte.com | 6 |  | 2020-01-16 | 2020-01-16
|  |  |  | Api Creation for dispay data having fields: 1. Total No. of Token Left 2. Total No. of Token Burn 3. Total No. of Token 4. Total No. of Fund Raised | py-aftabhussain@mobiloitte.com | 4 |  | 2020-01-17 | 2020-01-17
|  | Admin Profile |  | Api Creation for Admin Profile Name Email-Id Mobile No | py-aftabhussain@mobiloitte.com | 4 |  | 2020-01-17 | 2020-01-17
|  | Merchant Management |  | Api creation for display merchant data havinf Field: 1. Name 2. Emai ID 3. Mobile No 4. Merchant Id | py-aftabhussain@mobiloitte.com | 4 |  | 2020-01-18 | 2020-01-18
|  |  |  | Api Creation for Search merchant details by email and name | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-18 | 2020-01-18
|  |  |  | Api creation for reset the form data | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-18 | 2020-01-18
|  |  |  | Api creation for download merchant data into csv | py-aftabhussain@mobiloitte.com | 3 |  | 2020-01-20 | 2020-01-20
|  |  |  | Api Creation for Block a merchant | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-20 | 2020-01-20
|  |  |  | Api creatiob for display merchant details having Fields: 1. Name 2. Email Id 3. Merchant ID 4. Mobile No | py-aftabhussain@mobiloitte.com | 3 |  | 2020-01-20 | 2020-01-20
|  | Fee Managemenrt |  | Api Creation for display Transaction fee and Token creater fee | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-21 | 2020-01-21
|  |  |  | Api Creation for update Transaction fee and Token creater fee | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-21 | 2020-01-21
[5 empty] | py-aftabhussain@mobiloitte.com |  |  | 2020-01-21 | 2020-01-21
|  | Edit profile |  | Api creation for edit admin profile | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-21 | 2020-01-21
|  | Change Password |  | Api creation for change password | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-22 | 2020-01-22
py-aftabhussain@mobiloitte.com
| Merchant Panel | Basic Page |  | Template integration for SignIn | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-22 | 2020-01-22
|  |  |  | Template integration for Forget Password | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-22 | 2020-01-22
|  |  |  | Template integration for Reset Password | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-22 | 2020-01-22
|  |  |  | Template integration for Signup | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-23 | 2020-01-23
|  | Dashboard |  | Template integration for Create Token, Create Token, Token Management, Merchant Profile, Logout | py-aftabhussain@mobiloitte.com | 6 |  | 2020-01-23 | 2020-01-23
|  | Create Token |  | Api Creation for Create Token having fields: 1. Symbol image Field 2. Token Integer Field 3. No. of Token Integer Field 4. Register of Website URL field | py-aftabhussain@mobiloitte.com | 4 |  | 2020-01-24 | 2020-01-24
|  | Address Management |  | Api Creation for create wallet address | py-aftabhussain@mobiloitte.com | 4 |  | 2020-01-24 | 2020-01-24
|  |  |  | Api Creation for generate qr code | py-aftabhussain@mobiloitte.com | 3 |  | 2020-01-25 | 2020-01-25
|  | Toke Management |  | Api Creation for Token Management: Total Number of Token Total Number of Token burn Pending Token | py-aftabhussain@mobiloitte.com | 3 |  | 2020-01-25 | 2020-01-25
|  | Merchant Profile |  | Api Creation for Merchant Profile Name Email-Id Mobile No | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-25 | 2020-01-25
|  | Edit profile |  | Api creation for edit admin profile | py-aftabhussain@mobiloitte.com | 3 |  | 2020-01-27 | 2020-01-27
|  | Change Password |  | Api creation for change password | py-aftabhussain@mobiloitte.com | 3 |  | 2020-01-27 | 2020-01-27
|  | Logout |  | Api creation for Logout | py-aftabhussain@mobiloitte.com | 2 |  | 2020-01-27 | 2020-01-27